## PAP Template
Sustainability Victoria
SV Procurement Activity Plan 2022-23
No. | Procurement name | Category | Project | Description | Estimated invitation to supply release date | Market approach (ITS/RFQ/RFT/EOI/ SPC, open/selective) | International Agreement Covered procurement? Yes/No | Comments | Point of contact | Group
1 | RV - Supporting Victorian Councils Evaluation -Materials mapping | Research & evaluation | RV - Supporting Victorian Councils |  | 2022/23 | RFQ | No | Project delayed due to COVID, therefore evaluation procurement delayed til 2022/23. | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
2 | Recycling Victoria Infrastructure Plan building on IV analysis and integrating with SV data system | Consultancy (analysis & advice) | Recycling Victoria Infrastructure |  | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
3 | Recycling Victoria Infrastructure Plan Cost Benefit analysis of options for key materials | Consultancy (analysis & advice) | RV - Infrastructure Planning |  | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
4 | Recycling Victoria Infrastructure Plan Editing services | Professional Services | Recycling Victoria Infrastructure |  | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
5 | Auditor to develop auditing protocols and conduct audits for asbestos transfer sites | Professional Services | Asbestos Disposal Management Plan |  | 2022-07-01 | RFQ | No | Completed | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
6 | Training provider to develop and delivery training modules. | Professional Services | Asbestos Disposal Management Plan | Training provider to develop training modules to support development and operation of asbestos dispisal points. | 2023-09-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
7 | Infrastructure expert to conduct site assessments for full network roll out | Professional Services | Asbestos Disposal Management Plan | Infrastructure expert provider to to conduct site assessments for full network roll out of potential asbestos dispisal points. | 2023-06-01 | RFQ | No | TBC | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
8 | RV – Detox your Home Program | Professional Services | Household Collection Program |  | 2022-07-01 | Tender | No | Completed | Requestprocurement@sustainability.vic.gov.au | Community Action
9 | RV – Detox your Home Program | Professional Services | Household Collection Program |  | 2022-10-01 | RFQ | No | Completed | Requestprocurement@sustainability.vic.gov.au | Community Action
10 | RV - Waste Data New Data System Stage 2 | IT, web and data management | Recycling Industry Support |  | 2022-06-01 | eServices | No |  | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
11 | Multicultural community engagement | Marketing & Engagement | CE Education and Behaviour Change Program | Delivery of multicultural community engagement activities | 2022-12-01 | Marketing Services | No | Not confirmed if going ahead yet | Requestprocurement@sustainability.vic.gov.au | Community Action
12 | Program Evaluation and Social Research | Research & evaluation | CE Education and Behaviour Change Program | Delivery of multi-stage evaluation market research | 2022-12-01 | Marketing Services | No | Not confirmed if going ahead yet | Requestprocurement@sustainability.vic.gov.au | Community Action
13 | RV - Supporting Victorian Councils - Capacity Building forum | Professional Services | RV - Supporting Victorian Councils | Delivery of on-line forum by circular economy expert. | 2022-08-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
14 | FY24 State Budget bid support | Professional Services | n/a - SV wide initiative | The work will include combination economic analysis and research to support business cases that need to be developed as part of the State budget bid process. | 2022-10-01 | RFQ | No | The work will include combination economic analysis and research. | Requestprocurement@sustainability.vic.gov.au | People, Performance & Communications
15 | Organics Market Adoption Research Program | Professional Services | MAP - Organics | Research into the barrier to update and use of recycled organic products. | June 2023- June 2024 | RFQ | No | Likely to be multiple research projects and contracts under this program of work | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
16 | Program Evalution & Monitoring Framework | Professional Services | MAP - Organics | Engagement of consultant to set up M&E analysis for R&D -Organics projects | June 2023- June 2024 | RFQ | No | To set up M&E framework from grant recipents | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
17 | Buy Recycled Event - Procurement Toolkit | Professional Services | RV - Recycled First | Engagement of consultant to present at council workshop on using SV's Sustainable Procurement Toolkit | Sept 22 - March 23 | Selective | No | To developed toolkit and deliver workshop | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
18 | Sustainable Procurement Expertise | Professional Services | RV - Recycled First | Engagement of consultant to provide councils with 1:1 sustainable procurement expertise to embed sustainable procurement practices in council documentation | Oct - Dec 2022 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
19 | Water Authority Research | Professional Services | APPP - Accelerating Public Procurement Program | Engagement of consultant to identify and analysie opportunities and barriers for the procurement of recycled products for infrastruction and landscapring projects by Victorian water authorities. | 2022-09-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
20 | Buy Recycled Service Champion Program | Professional services, transport and catering | RV - Recycled First | Events delivered as part of Champion program to develop and upskill councils. Costs may include guest speakers, transport for site visits and event catering. | Oct 22 - June 23 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
21 | Buy Recycled Directory - long term strategy | Professional services | RV - Recycled First | Investigate and determine the approach for the long-term delivery of the Buy Recycled Directory, which may include commercialisation | 2023-06-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
22 | Buy Recycled Service - tool development | Professional services | RV - Recycled First | Development of additional sustainable procurement tools and resources to be housed on Buy Recycled Service website. | 2023-03-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
23 | Materials Market Research Part 1 | Professional Services | MAP - Materials | Engagement of consultant to undertake a key research piece into the markets for recycled materials - scope TBC | Oct 22 - Dec 22 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
24 | Materials Market Research Part 2 | Professional Services | MAP - Materials | Engagement of consultant to undertake research piece into the markets for recycled materials - scope TBC | Jan 23 - June 23 | RFQ | No | Potentially multiple research projects and contracts under this program of work | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
25 | Event management | Marketing & Engagement | CE Education and Behaviour Change Program | Management of public events | 2022-11-01 | Marketing Services | No | Not confirmed if going ahead yet | Requestprocurement@sustainability.vic.gov.au | Community Action
26 | Public Relations campaign delivery | Marketing & Engagement | CE Education and Behaviour Change Program | Management of public relations campaign activity | 2022-11-01 | Marketing Services | No | Not confirmed if going ahead yet | Requestprocurement@sustainability.vic.gov.au | Community Action
27 | Advertising procurement | Marketing & Engagement | CE Education and Behaviour Change Program | Advertising through MAMS agreement | 2023-03-01 | MAMS | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
28 | Creative production and translation services | Marketing & Engagement | CE Education and Behaviour Change Program | Production of design and creative for campaigns, translation of collateral | 2023-11-01 | Marketing Services | No | Not confirmed if going ahead yet | Requestprocurement@sustainability.vic.gov.au | Community Action
29 | Website development | Marketing & Engagement | CE Education and Behaviour Change Program | Design and build of campaign web products | 2023-11-01 | Marketing Services | No | Not confirmed if going ahead yet | Requestprocurement@sustainability.vic.gov.au | Community Action
30 | Recovered spoil - State of the Market | Professional Services | Spoils Management Strategy (SMS) - Initiative 15 | Engage a consultat to gather data and insights to produce a high-level state of the market report focussing on recovered spoil | Mar - July 23 | RFQ | No | Likely to be a further research project and contracts under this program | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
31 | 7 star homes behavioural insights work | Professional Services | 7 star homes | Engage the research services required to run the trial | Mar - June 23 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure (from April with the new structure)
32 | ResourceSmart Schools 2024-26 | Professional Services | ResourceSmart Schools | Delivery of the ResourceSmart Schools program to schools across Victoria | Feb-March 2024 | RFT | No | Not yet confirmed and dependant on the sucessful budget bid in the 2023 State Budget including timeframe and funding amounts | Requestprocurement@sustainability.vic.gov.au | Community Action
33 | PMO Strategy | Professional Services | PMO Strategy | Develop a PMO strategy | 2023-04-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | RC and PMO
34 | First Nations Engagement Strategy | Professional Services / Marketing & Engagement | CE Education and Behaviour Change Program | Engage a specialist agency to develop and deliver a First Nations engagement strategy for the Small Acts, Big Impact campaign | 2023-06-01 | RFQ | No | Not confirmed if procurement is going ahead this financial year or next | Requestprocurement@sustainability.vic.gov.au | Community Action
35 | Board Performance Assessment | Professional Services | Board | Administration of a Board Performance assessment and review | 2023-06-01 | RFQ | No | Not yet confirmed and will likely commence next financial year - 30% of total cost due on commencement of project, 30% due on delivery of Board report and 40% due on completion. | Requestprocurement@sustainability.vic.gov.au | Office of the CEO
36 | Board Governance review | Professional Services | Board | Full review and re-write of Board Governance documents - Charter, Operating manual, policies | 2023-05-01 | RFQ | No | Review is underway (as at March 2023) | Requestprocurement@sustainability.vic.gov.au | Office of the CEO
37 | ELT Strategic Offsite | Professional Services | Executive Leadership Team | Two day facilitated strategic workshop setting SV's 23/24 priorities aligned with growth areas and SV2030 | 2023-07-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Office of the CEO
38 | World Circular Economy Forum Helsinki |  | CEO | International Forum focusing on nature-positive future, showcasing global change makers and building the capacity to collaborate. | 2023-05-22 |  |  | Circa | Requestprocurement@sustainability.vic.gov.au | Office of the CEO