## PAP Template
Sustainability Victoria
SV Procurement Activity Plan 2022-23
No. | Procurement name | Category | Project | Description | Estimated invitation to supply release date | Market approach (ITS/RFQ/RFT/EOI/ SPC, open/selective) | International Agreement Covered procurement? Yes/No | Comments | Point of contact | Group
1 | RV - Supporting Victorian Councils Evaluation -Materials mapping | Research & evaluation | RV - Supporting Victorian Councils |  | 2022/23 | RFQ | No | Project delayed due to COVID, therefore evaluation procurement delayed til 2022/23. | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
2 | Recycling Victoria Infrastructure Plan building on IV analysis and integrating with SV data system | Consultancy (analysis & advice) | Recycling Victoria Infrastructure |  | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
3 | Recycling Victoria Infrastructure Plan Cost Benefit analysis of options for key materials | Consultancy (analysis & advice) | RV - Infrastructure Planning |  | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
4 | Recycling Victoria Infrastructure Plan Editing services | Professional Services | Recycling Victoria Infrastructure |  | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
5 | Auditor to develop auditing protocols and conduct audits for asbestos transfer sites | Professional Services | Asbestos Disposal Management Plan |  | 2022-07-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
6 | Training provider to develop and delivery training modules. | Professional Services | Asbestos Disposal Management Plan |  | 2023-04-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
7 | Infrastructure expert to conduct site assessments for full network roll out | Professional Services | Asbestos Disposal Management Plan |  | 2023-04-01 | RFQ | No | TBC | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
8 | RV – Detox your Home Program | Professional Services | Household Collection Program |  | 2022-07-01 | Tender | No | Closing date 2 Spetember 2022 | Requestprocurement@sustainability.vic.gov.au | Community Action
9 | RV – Detox your Home Program | Professional Services | Household Collection Program |  | 2022-10-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
10 | RV - Waste Data New Data System Stage 2 | IT, web and data management | Recycling Industry Support |  | 2022-06-01 | eServices | No |  | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
11 | Recycling Victoria PR | Marketing & Engagement | Campaigns |  | TBC | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
12 | Recycling Victoria Phase 2 Creative | Marketing & Engagement | Campaigns |  | TBC | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
13 | RV - Supporting Victorian Councils - Capacity Building forum | Professional Services | RV - Supporting Victorian Councils | Delivery of on-line forum by circular economy expert. | 2022-08-01 | RFQ | No | Very small expert talent pool, direct RFQ. | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
14 | FY24 State Budget bid support | Professional Services | n/a - SV wide initiative | The work will include combination economic analysis and research to support business cases that need to be developed as part of the State budget bid process. | 2022-10-01 | RFQ | No | The work will include combination economic analysis and research. | Requestprocurement@sustainability.vic.gov.au | People, Performance & Communications
15 | Organics Market Adoption Research Program | Professional Services | MAP - Organics | Research into the barrier to update and use of recycled organic products. | Oct 2022- June 2024 | RFQ | No | Likely to be multiple research projects and contracts under this program of work | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
16 | Program Evalution & Monitoring Framework | Professional Services | MAP - Organics | Engagement of consultant to set up base and M&E framework for CE Markets Fund - Organics | Sept - Dec 2022 | RFQ | No | To set up M&E framework from grant recipents | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
17 | Buy Recycled Event - Procurement Toolkit | Professional Services | RV - Recycled First | Engagement of consultant to present at council workshop on using SV's Sustainable Procurement Toolkit | Sept 22 - March 23 | Selective | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
18 | Sustainable Procurement Expertise | Professional Services | RV - Recycled First | Engagement of consultant to provide councils with 1:1 sustainable procurement expertise to embed sustainable procurement practices in council documentation | Oct - Dec 2022 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
19 | Water Authority Research | Professional Services | APPP - Accelerating Public Procurement Program | Engagement of consultant to identify and analysie opportunities and barriers for the procurement of recycled products for infrastruction and landscapring projects by Victorian water authorities. | 2022-09-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
20 | Buy Recycled Service Champion Program | Professional services, transport and catering | RV - Recycled First | Events delivered as part of Champion program to develop and upskill councils. Costs may include guest speakers, transport for site visits and event catering. | Oct 22 - June 23 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
21 | Buy Recycled Directory - long term strategy | Professional services | RV - Recycled First | Investigate and determine the approach for the long-term delivery of the Buy Recycled Directory, which may include commercialisation | 2023-06-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
22 | Buy Recycled Service - tool development | Professional services | RV - Recycled First | Development of additional sustainable procurement tools and resources to be housed on Buy Recycled Service website. | 2023-03-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
23 | Materials Market Research Part 1 | Professional Services | MAP - Materials | Engagement of consultant to undertake a key research piece into the markets for recycled materials - scope TBC | Oct 22 - Dec 22 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure
24 | Materials Market Research Part 2 | Professional Services | MAP - Materials | Engagement of consultant to undertake research piece into the markets for recycled materials - scope TBC | Jan 23 - June 23 | RFQ | No | Potentially multiple research projects and contracts under this program of work | Requestprocurement@sustainability.vic.gov.au | Industry & Infrastructure