## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Resource Smart Schools (RSS) | Program | RSS is a program delivered through schools to access skills, knowledge or capabilities to systematically address or monitor sustainability on their campus, in their curriculum and in their community. | For Review | Yes | With limited funding available for GIA improvements, a gender equity lens was applied to program event planning for 2023. As a result of completing the GIA for the program for the first time as part of the 2023-2024 ERC budget bid process, changes to program events included: - Female Master of Ceremonies contracted to host the 2023 RSS Awards ceremony. - Program services such as professional learning events are held outside of core teaching hours, not run during lunch breaks and ourside of core school pick up times. - Video recordings of professional learning events are available on request - Development of templates to assist participants in the completion of program actions and tasks. | Yes | Application of gender and intersectional lens was applied to program outputs in the RSS 2024-25 program budget submission and will include an intersectional lens to: - how gender roles impact a person's ability to participate in the suite of RSS program activities, and - how do other intersactional factors impact on people's ability to participate in the program and promote participation in program activities in their school community.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Leadership assessment tool (LSI) used to understand leadership impact. | Complete | The Life Styles Inventory (LSI) was delivered to 70 people leaders across Executive, Senior Managers and Team Leader cohorts as part of the Leadership Development Program called Leading with Impact. This included a 360 feedback process with an individual debrief for each leader. The process provided individual insight into leadership styles and their impact on direct reports, peers and the individual's people leader. The leadership development program as well as the individual LSI experience provided the opportunity for leaders at all levels of SV to understand the impact of their role in creating an inclusive and engaged environment and culture for all employees. This phase of the Leading with Impact Program has been completed. | SV's GEAP has four key Goals - the first is Gender Responsive Leaders with Impact. This includes gender equal, diverse and responsive leadership. A key measure of this overaraching goal is People Matter results. SV's People Matter results continue to show a positive and engaged workforce with the index increasing by 2 points to 78 since 2022. The areas that rated the hightest include questions relating to Senior Leadership (82%), Cultural safety (96%) and Flexible Working (97%). | This is an annual survey with key action items in response to the survey results being ongoing actions. | People and Culture and Leadership Team | X |  |  | X
Align SV's Cultural aspirations with commitment to gender equality, diversity, and inclusion ongoing. | Ongoing | SV continuously aspires to strengthen its cultural aspirations in alignment to its commitment to gender equality, diversity and inclusion. SV's cultural aspirations clearly articulate a focus on a OneSV culture where diverse individuals work collaboratively to achieve shared goals. Being bold and courageous is another SV value that encourages new ideas and thinking differently. Over the next 24 months, SV will review and refresh these aspirations, further refining the connection to gender equality, diversity and inclusion. | The People Matter survey and key questions within the survey | SV's values and behaviours are under review in 2024 - there will be a focus to ensure any revised values are embedded across the organisation (eg. recruitment and onboarding to performance and award and recognition). This action should be completed by June 2024. | People and Culture and Leadership Team | X |  |  | X |  |  | X
Review of SV policies. | Ongoing | The P&C team regularly review policies and update or revise to remove gendered language and any connotation of exclusion. In 2023, SV also introduced a new policy for Menstruation and Menopause (M&M) Wellbeing which includes additional leave provisions for employees who were experiencing symptoms of menstruation or menopause that impacted their ability to work. This policy has received support and endorsement from employees and the Board. It has also received positive attention from many organisations across the VPS and in the private sector as being progressive and addressing some of the underlying elements of gender equality. | While the practice of reviewing policies is ongoing, the introduction of the M&M Wellbeing policy was specifically introduced to address specific experiences that impact individual's abilitiy to work and may also have impacts on other career decisions. This policy directly links to the promotion of gender equality by addressing some of the barriers and stigma. The policy has been widely supported across the organisation and has attracted interest by other VPS and private sector organisations that are interested in addressing some of the underlying issues of gender equality through innovative policy. The uptake of the leave by 17 employees is a positive reflection of that introduction of the policy addressed underlying barriers/stigma in relation to this area. | This is an ongoing practice for the P&C team with each policy having a date by which it is required to be reviewed. There is also an organisation wide audit and review of all internal policies being conducted which commenced in January 2024. | People and Culture | X |  |  |  |  | X
Strengthen links between GEAP, SV People Strategy, and SV2030. | In progress | SV2030 (SV's strategy) and the People Strategy are intrinsically linked to the promotion, awareness and understanding of diversity and inclusion by ensuring that the work SV does considers the impact of gender and intersectionality. This is especially important as SV's key programs of work can have a direct and meaningful impact on households, communities, schools and industry. This work is currently in progress as the People Strategy and SV's Strategic Plan are reviewed and designed for the next three years. | Program evaluation will be built into the overall program design. Quarterly Operational Performance Reports will be an initial lead measure. | By June 2024 | People and Culture, Strategic Planning and Performance and Leadership Teams | X |  |  |  | X
Transparent data and communication supported across the organisation. | Ongoing | Annual all staff update on key indicators. Quarterly reporting to the Executive and Senior Leadership team of key people data. | Transparent data and communication is a key practice across SV with regular reporting providing insights to progress across all indicators. Context and organisational change will need be considered when reviewing progress against key indicators. | This is an ongoing practice with existing and regular timelines. | People and Culture and Strategic Planning and Performance Teams | X | X | X | X | X | X | X
Include intersectional gender equality in SV research and policy development. | In progress | Designing of the three-year strategy will incorporate an intersectional lens. Too early to provide further detail at this time. | Too early to evaluate at this stage. | 2026-06-01 | Strategice Planning and Performance and People and Culture
Ongoing Board and Executive engagement through quality reporting on progress and actions. | Ongoing | Annual update to the Board and Executive on the progress across the indicators as well as key actions in the GEAP. | Success in regular and transparent reporting. | Next report due February 2024 | People and Culture and Executive Leadership Team | X | X | X | X | X | X | X
Develop our EVP to position SV as an employer of choice with opportunities for staff of all genders, abilities, racial and cultural backgrounds. | In progress | In 2023, SV achieved the first place in the AFR BOSS Best Places to Work awards as well as the HR Director 5 Star Employer of Choice Awards. A key element of the submission was a staff survey that sought insights into SV's culture and inclusion practices. SV will continue to strengthen its EVP in 2024 through engaging and consulting with staff and implementing continual enhancements to its culture and offerings. | The key indicators of success are: People Matter Survey results (SV's engagement has increased by 2 points in 2023) and results from the survey for AFR BOSS Best Places to Work. | By December 2024 | People and Culture | X |  |  |  | X
Review recruitment practices to deliver intersectional diversity, inclusion and gender equality in the workforce. | Ongoing | SV's recruitment practices have been refreshed to ensure that hiring managers are provided with coaching on unconscious bias, need to disclose any conflicts of interest and follow JSE guidelines strictly. This is an ongoing practice. Currently, SV employees have an opportunity to update the HR information system with their diversity data to assist with providing insights into the intersectional landscape of SV - under 10% of employees have provided this data which makes an assessment of progress in this space difficult to report. | Success in this area can be measured by People Matter results, specifically questions relating to diversity and inclusion. | By December 2024 | People and Culture and Hiring managers |  |  |  |  | X
Ensure all recruiting and line managers undertake relevant training including unconscious bias in recruitment and performance appraisal. | Ongoing | Current practices include coaching on unconscious bias and training during the recruitment process, mid-year and end of year performance appraisals. Next steps would include designing an e-learn module for all people leaders/hiring managers to complete to increase awareness in this space. | The design of the e-learn and regular refresh for all hiring managers is an ongoing evaluation measure. | E-Learn to be designed by December 2024. | People and Culture and Hiring managers | X |  |  |  | X
Improve onboarding data collection to better capture intersectional gender data. | Ongoing | SV has recently updated their Human Resources Informantion System (HRIS) which has also included additional provision for employees to voluntairly update their personal data (eg. gender, sexuality, cultural background, religion etc.). Ongoing communication to encourage employees to update their information while balancing individual privacy. | Reviewing the change in the amount and type of intersectional data, following the system | Ongoing | People and Culture and all employees | X | [5 empty] | X
Review current systems (HRIS) to improve data collection practices. | In progress | As above | The implementation of the new HRIS alone will not ensure that employees update all of their personal details. While the system has the functionality to hold and report on intersectional data, it will be an ongoing conversation with employees for them to feel comfortable with sharing personal data (that may also be used for broader reporting purposes). | Ongoing | People Culture |  |  | X |  |  | X | X
Better understand SVs workforce diversity to establish our current state. | Ongoing | As a small and dynamic organisation, SV's workforce diversity can reflect the changing landscape. While there is a data regarding the gender composition and age, the approach to collecting broader diversity data is ongoing. This data is volunteered by employees which make it challenging to get a holistic view of the organisation. Keen to understand how other VPS organsiations collect this data. | Data available in the HRIS. | Ongoing | People and Culture and all employees | X
Annual Reporting on Workplace Diversity and Sexual Harassment Cases and Experiences (Quantitative and qualitative). | Complete | There is zero tolerance for sexual harassment or discrimination on the basis of gender or any other basis at SV. People Matter data provides annual insight into both the quantitative and qualitative data while quarterly reporting thorugh a Wellbeing Health and Safety lens also provides an insight into informal concerns and formal complaints. Both types of claims will be reviewed and investigated with the strictest of confidentiality, sensitivity and robustness. | People Matter Survey results, informal and formal complaints (through internal or external chanels), themes from EAP (deidentified). | Quarterly and annually. | People and Culture and all employees |  |  |  | X |  | X
Promote safety and integrity of internal complaint making systems to maintain low levels of sexual harassment, bullying and discrimination. | Complete | The People and Culture team have a secure inbox that is dedicated for employees to send confidential queries or concerns that would be reviewed, investigated and responded to within 24 hours (depending on the complexity of the query). Employees also have the option to contact an independed mediator and EAP to raise any issues. The promotion of safety and integrity especially in relation to sexual harassment, bullying and discrimination is led from the top with SV's iCEO providing their committment to zero tolerance of behaviours that breach the values, behaviours and code of conduct. 'Workplace behaviours' workshops are run for all employees to refresh them on the definitions, expectations and implications on misaligned behaviours. | Reporting - informal and formal complaints and People Matter results and feedback are key indicators of success. | Complete for FY 2023/24 but ongoing | People and Culture, Leadership Team |  |  |  | X
Create Gender Pay Equity / Remuneration Policy & Governance Structures/ Committee to oversee reduction. | Not started | The approach that SV will take to address this area of governance and policy may need to be reviewed in the near future. Based on the data analysis, SV's gender pay gap continues to remain low and the reason for the gap can be understood for that period of time, as a dynamic and relatively small organisation. While the gender pay gap will continue to be analysed and reported on, SV will consider other approaches to addressing any specific gaps in a more targeted and pragmatic way. Prior to embarking on this work, SV would like to research and understand how this is being approached across the VPS and work on a collective appraoch. This is also an opportunity to receive guidance from the Gender Equality Commission regarding what would be considered the parameters for a 'reasonable tolerance level', given other factors within the organisaiton (eg. Size of organisaiton, gender composition across all levels). | Too early to gauge | This may need to continue into the next GEAP | People and Culture and Executive Team |  |  | X
Design policies that ensure this [gender] gap is addressed. | Not started | As above | Too early to gauge |  |  |  |  | X
Gender Pay Equity Target Framework & Policy. | Not started | As above | Too early to gauge |  |  |  |  | X
Explore budget to invest in a Gender Pay Equity/Remuneration Budget. | Not started | As above | Too early to gauge |  |  |  |  | X
Budget for longer term support for Gender Pay Equity/Remuneration Governance. | Not started | As above | Too early to gauge |  |  |  |  | X
Budget for identified gender pay inequities. | Not started | As above | Based on the base line data and 2022/23 gender pay gap, this is not an area of signigicant concern for SV. The focus will continue to be on ensuring SV's recruitment practices and remuneration remain transparent and fair. | Ongoing focus to ensure this practice is embedded. |  |  |  | X
Strengthen Diversity and Inclusion Plan to include Gender Pay Equity. | In progress | The GEAP will continue to be the key plan for SV relating to Gender Equity. SV's Diversity and Inclusion Action Plan will reference and link to the initiatives outlined in the GEAP to ensure focus and removal of duplication. | Clear outline of activities and reference to the GEAP in the Diversity & Inclusion plan
Develop guidelines for recruitment & promotion to maintain gender equity in base salary, performance bonuses and other entitlements. | Complete | SV's recruitment and promotion guidelines are aligned to the broader VPS requirements and values. Clear and transparent process are in place for higher duties opportunities. Progression eligibility is aligned with the VPS eligibility requirements, ensuring consistency, transparency and fairness. | Guidelines have been developed and available on the intranet. Annual training on progression eligibility requirements are conducted each year. These practices are embedded into BAU. | Completed | People and Culture |  |  |  |  | X
Improve internal gender gap data analysis and research gender pay gap in the sustainability sector. | In progress | Ongoing review/analysis of SV's gender pay gap has commenced and regular reporting to ELT and Board. Integrating the insights gained from the GIAs has been helpful to understand the gendered landscape of the sustainability sector. This work will need to be further scoped and will be an ongoing focus for this and furure GEAPs. | Building templates and dashboards to regularly report on the gender pay gap (currently in progress) will create some efficiencies in this space. | 45444 | People and Culture and Strategic Planning and Performance Teams |  |  | X
Deepen data insights and analysis to identify ways to address imbalances and close the gap. | In progress | The introduction of the new HRIS will provide deeper insight into the pay gap and the underlying reasons. While SV has a small gender pay gap, there is opportuity to understand what contributes to this. SV's gender composition is 70% female with many of the roles at level 3 and 4 predominantely filled by female employees. SV is a relatively small agency and has significant movement in any given year. There could be other contributing factors for the pay gap however it is not significant enough to be linked to systemic decisions or practices. | Implementation of the HRIS as a starting point. Use data and insights to inform, support and address imbalances across specific scenarios (as they arise). | Ongoing focus to ensure this practice is embedded. | People and Culture and Executive Team |  |  | X |  | X
Improve systems to collect quality gender disaggregated data. | In progress | SV has introduced a new HRIS which will support the collection of quality gender disaggregated data (provided individual employees are comfortable to update this information in the system). | A measure of success will include increased use and updating of diversity data by employees. | Ongoing
Research and understand contributing factors to the SV gender pay gap. | In progress | As indicated above, as a smaller agency, the pay gap can be impacted by small movements across the organisation. Understanding the broader factors that contribute to the gender pay gap across the VPS will also be helpful to address the systemic contributors to the pay gap. The gender composition at SV can play a contributing factor to the overall pay gap however further analysis at each level would provide an better insight into what particular areas to focus. | Regular reporting on the gender pay gap to track trends. | Ongoing | People and Culture, Diversity and Inclusion Network |  |  | X |  | X
Sharing of gender remuneration data and workplace experience data to all staff. | Complete | While this is an annual practice, SV is transparent with sharing data about the pay gap and People Matter results. | Results shared and available for employees to access. | Quarterly and annually. | People and Culture and Strategic Planning and Performance Teams
Continue to strengthen our leading approach to flexibility, ensuring all employees feel supported and empowered to successfully manage work and life commitments. | Complete | Flexible working practices continues to be SV's key strength. It provides a working environment that provides employees to be engaged and productive. Flexibility was one of the key strengths that contributed to SV's number one ranking at the AFR BOSS Best Places to Work. | People Matter Survey results, Wellbeing survey results | Ongoing | People and Culture, Leadership Team | [5 empty] | X
Build flexibility as a cornerstone of SVs EAP | Complete | As above | People Matter Survey results, |  | People and Culture |  |  |  |  | X | X
Ensure equal access to flexible work arrangements for all employees, including those with family and carer responsibilities, and continue to build positive perceptions about flexible working practices. | Complete | As above | People Matter Survey results |  | People and Culture and Leadership Team | [5 empty] | X
HR policies streamlined to fully support flexible workplace practice – Find Your Flex. | Complete | SV introduced the Find Your Flex policy outlining the many ways that all employees could work, access various leave types and balance their personal and professional commitments. The policy has been successfully implemented and embedded into working practices. Over 50% of SV employees have a flexible working arrangement in place. | Reporting - informal and formal complaints and People Matter results and feedback are key indicators of success. | [7 empty] | X
Best Practice Leave provisions supporting shared and gender equal care. | Complete | SV's leave provisions relating to gender equal care are reflective of the VPS EBA. In addition to this, SV introduced the Menstruation and Menapause wellbeing policy, providig additional leave days for those impacted by symptoms of menstruation or menopause to access leave without the requirement to provide a medical certificate. | People Matter Survey results |  | People and Culture and Leadership Team | [5 empty] | X
Implementation plan to support SV’s Wellbeing, Health, and Safety (WHS) Strategy. | Complete | SV’s WHS strategic plan was implemented in February 2023 with a planned end date of December 2024. The plan to date is 84% complete with items outstanding due to delays in the implementation of our new HRIS (Human Resource Information System), as well as ongoing delays in implementing Victoria’s amendment to the OHS Act (Psychological Health). The primary activities completed to date include actioning SV’s 2021 OHS Audit (23 actions), enacting Victoria’s 11 Child Safe Standards, implementing education, awareness and support for the psychological safety and mental wellbeing of SV employees - noting in 2023 81% of EAP sessions were utilised by females and 19% males, and ensuring OHS framework was available to SV including OHS policies and procedures, and a robust consultative process. To date regular reporting is conducted with Monthly WHS Updated to our senior leadership groups which includes our prescribed lag and lead OHS metrics from our WHS Strategy. Trends are monitored closely and are reported on a quarterly basis in our Organisation Performance Report which is provided the board and shared organisation wide. | An increase in hazards reported and corrective actions identified and completed indicates SV’s shift in WHS culture to a proactive and preventative approach to keeping SV employees safe. Several surveys have been conducted since the implementation of our WHS Strategic Plan, including the VPS People Matters Survey (2023) which saw an organisational increase year on year in our results with employees feeling physically safe at work, less employees having negative emotions and experiencing work stress, and a positive increase in our psychosocial safety climate. | [5 empty] | X |  | X
Refreshed onboarding practices which include flexible workplace opportunities and all leave options articulated (EVP). | In progress | SV's onboarding process and induction articulate the available flexible working options for all employees. This message will also be incorporated into the EVP. The 2023 People Matter results also reflects a very positive uptake and acknowledgement of these practices. The EVP will be a strategic focus over the next year for SV. | People Matter Survey results continuing to remain strong | [7 empty] | X
Better understand the link between flexibility and career progression to ensure all opportunities are wholly available and obtainable. | In progress | Ensuring that flexibility is not a barrier to career progression is supported by the key priciples in the Find your Flex policy. SV also has examples of leaders that job share at the Executive, Senior Leader and Team Leader levels. These provide working examples of flexibility and career progression. Other flexible working options that are accessed across all levels of the organsation is compressed hours. | People Matter Survey, number of flexible working arrangements across all levels of the organisation | Ongoing | People and Culture and Leadership Team | [5 empty] | X
| Select one | Ao above
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
The strategies and measures in the GEAP are predominantly implemented by the People and Culture team with the support of the Gender Equality and other Diverstiy and Inclusion working groups (made up of voluntary employees). Each working group has an Executive sponsor. The working group memebers also support project leads with GIAs. There is one key role in P&C that leads the GEAP work with other team members providing expertise in data analysis and policy development and implementation. While this level of resourcing is sufficient for the size of the organisation, additional temporary support may be needed for the design of the next GEAP (dependent on the requirements set out by the Commission and insights from the data analysis).

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | SV's baseline data reflected a gender composition with 69% women and 31% men. 68% of leadership roles were held by women and 32% by men. In 2023, SV's overall gender composition is 71% women and 29% men. Across VPS levels 3 to 6, the proportion of women in the workforce decreases as the VPS level increases. The exception is VPS7 and SES1 however these two cohorts have smaller numbers for analysis and reporting. The majority of SV employees are at VPS levels 4 and 5 with the gender composition for VPS4 being 77% women and VPS5 is 68% women. At the VPS6 level, there are 63% women. All VPS6 and many VPS5 roles are lead or manager roles. The gender composition has remained similar to the baseline data across the whole organisation and across each level of the organisation (69% women and 31% men). Since the 2021 results, 87 new employees joined SV. The proportion of women in leadership positions is below the overall proportion of women however the majority of leadership positions are held by women (59%). SV continues to be an organisation with positive representation of women at all levels of the organisation, with the majority of Executive and Senior Leadership roles held by women. As a small and dynamic organisaiton, small changes and movements can impact percentages however overall, SV's gender composition at all levels reflects positively towards women. | Yes | No | No | No | No | No | No | As a relatively small and dynamic agency, SV's employee numbers fluctuate over the years to support the delivery of key projects. In the 2022/2023 year, SV went through considerable growth. During this time, the gender composition of the workforce did not materially shift. The focus in the future will also include the intersectional lens.
Gender composition of governing bodies | Yes | At 30 June 2023 SV's Governing Body (the Board) consists of eight members, four women and four men. One member departed between the 2022- 23 year and no new members were recorded during this time. In the 2020-21 data, the Board composition was four women and six men. | No | No | No | No | No | No | No
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | SV's 2023 data indicates that remuneration for work of equal or comparable value shows slight variances across the levels. SV's Executive Leadership Team has pay parity across the cohort (not including the CEO). At VPS level 3 there is a gap in favour of women by -7.7% and at VPS level 4, there is a gap of 1.6% in favour of men. Level 5 has significantly more women than men however the pay gap is 3% in favour of men. Managers at level 6 where there are under half the number of men than women have a -2.6% gap in favour of women. Level 7 has a pay gap of 3.6% in favour of men. Due to the small numbers in this cohort, further analysis/information would easily identify individuals. It can be stated that in this cohort, each role has a specialised and nuanced focus which makes direct comparison of the roles difficult. SV's gender composition across the organisation and across each of the levels also contributes to the organisational-wide pay gap of 3.5% (excluding the CEO salary). This has remained consistent from the baseline data. The baseline data indicated no overall gender pay gap across SV when using the median base salary. There was gender pay gap of 1.8% when considering the average salary. The change in employee numbers and a change in CEO has impacted and shifted the basline numbers in 2023 with the median salary having a gender pay gap of 2.7% and the mean salary gender pay gap increasing to 6.7% (and 3.5% excluding the CEO salary). While these numbers have increased overall, SV can identify contributing factors to this increase. Regular reporting and trend analysis of these figures will provide a better indication of any systemic concerns however at this stage of reporting the rational for these numbers is understood. | Yes | No | No | No | No | No | No | There are small number of people at some levels of the organisation that may contribute to the gender pay gap however further analysis will identify individuals.
Sexual harassment in the workplace | Yes | There were no reported sexual harassment incidents at SV in the two reporting periods. SV strongly maintains a zero tolerance approach to all discrimination, harassment and sexual harassment. Training for all staff is provided on an annual basis and during induction, ensuring all employees are aware of their responsibilities, rights and avenues to raise any concerns both informally and formally. SV continues to proactively support employees with awareness of their rights and the various confidential formal and informal reporting avenues. SV's people experience data states that 97% agree that the organisation encourages respectful workplace behaviours and 85% says the organisation takes steps to eliminate bullying, harassment and discrimination (up by 17% from the previous year) and feel safe to challenge inappropriate behaviour (up by 6% from last year). While no formal complaints were received, the 2023 People Matter Survey results indicated that 2% of employees may have experienced or witnessed an incidence of sexual harassment. No further details were available through the survey results to gain further understanding of the results. This data was proactively reviewed and while respecting the anonymity of the process, the results and process employees could take to get support were transparently shared. The process created a safe space for the broader context of the situation to be confidentially shared with P&C and proactive steps were taken to address the situation with all employees' safety in mind. | No | No | No | No | No | No | No
Recruitment and promotion practices in the workplace | Yes | Recruitment: For our 2021 audit, SV did not collect specific recruitment data however historically, SV's gender composition (reflecting its recruitment practice) has always indicated a majority of women recruited to roles across all levels of the organisation. Since 2021, there were 48 new employees, 67% are women. The majority of new starters are in VPS4 and VPS5 roles. There were also senior appointments at VPS 6.2, VPS7 and SES1 which were all women. We were unable to collect consistent intersectional data for both the baseline report as well as this progress report. Since the base line report, we have embarked on updating the payroll system and through this process have commenced encouraging employees to voluntarily update their data in the system - this continues to be an area of focus in the future. Since the 2021 People Matter results, SV has updated its recruitment processes, established clear and consistent guidelines, providing hiring managers with coaching and education on the JSE policy and best practice recruitment standards. Included in all job advertisments is a statement around welcoming applications from diverse backgrounds: "At SV we are building an accessible and inclusive workforce. We want to attract and retain people of all genders, ages, disability, sexual orientation, family and caring responsibilities, and cultures including people of Aboriginal and Torres Strait Islander heritage. We aim for an inclusive workplace that makes every employee feel valued while also acknowledging their differences and how these differences contribute to the organisation's culture and business outcomes. If you require a copy of this advertisement and attached documentation in an accessible format or would like to discuss an access requirement/reasonable adjustment for the recruitment process, please contact the Recruitment Team." Flexibility and being voted AFR BOSS Best Place to Work in the Government and Education section, reflecting a strong values-based and inclusive culture along with purposeful work are integral to the recruitment and promotion practices at SV. Promotions and Higher Duties: Since the 2021 base line audit, 10 employees were promoted and 44 performed in higher duties. Eight women were promoted and 33 acted in higher duties over 2022 and 2023. The higher duties policy was refreshed to provide clear guidelines for internal secondment advertisments, providing visibility of opportunities across the organisation. | No | No | No | No | No | No | Yes | A concerted effort was made to refine and update processes and policies around recruitment and promotion opportunities in response to the the People Matter Survey results.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | SV has always had generous and progressive flexible working practices and the People Matter Survey results have reflected this in the employee's experience. The introduction of Find Your Flex policy, Summer Hours, Family Violence policy and Ways of Working practices have provided employees with the support and framework to work in an environment that is best suited to their work while balancing individual caring and family needs. Carer's Leave and Parental Leave: Over the 2022-23 year, 53 employees accessed carers leave with 72% being women and 28% men (this is reflective of the overall gender composition of the organisation). As a proportion of the organisation, a similar proportion of each gender took carers leave with 22% of all women and 21% of all men taking carers leave. With parental leave, nine employees took this leave with a relatively even distribution of women (4) and men (5). Menstruation and Menopause Wellbeing Leave: SV also introduced menstruation and menopause leave with three additional days of leave for individuals experiencing symptoms that may impact their ability to work. This leave has been utilised by 7% of employees with a total of 112 hours of leave taken. This policy has been instrumental in starting broader discussions about the some barriers that individuals can face and has de-stigmatised the topics in a work context. Flexible Working Arrangements: 58.1% of all women and 45.7% of men at SV had a formal flexible working arrangement. Of this percentage, 87% of women and 13% of men work part-time. 72.9% of women and 27.1% men utilised compressed hours as a flexibility option. Other: SV has a family violence leave policy providing employees with the support and leave they need. During this reporting period, no leave was taken. SV's Ways of Working guidelines outline the expectations of broader flexible working practices. This includes expectations of cadence of team and 1:1 meeting, team anchor days and attending events in-person, on-line or in a hybrid manner. | No | No | No | No | No | No | Yes | Promoting flexible working practices and the introduction of a new policy were key strategies to support this indicator.
Gendered segregation within the workplace | Yes | In 2021, the gender composition varied across occupations. Noting there were fewer staff across more occupation categories in 2021 made it difficult to draw conclusions about segregation. Most occupations (with more than 5 staff) had similar gender composition to the overall SV composition (ie 71% women, 29% men). The exceptions were: Public Relations Professionals (91% women and 9% men) and Specialist Managers with a 50% men and 50% women composition. In the 2023 data, the gender composition varies considerably for the top 5 occupation categories from 50% women for Specialist Managers to 91% for Public Relations Professionals. Women occupy double the number of roles in the Program or Project Administrator category however there remains a gender pay gap. In the Specialist Managers category, where there is an even gender distribution, there is a pay gap in favour of women. Please note: Only the top 5 ANZSCO occupation categories at SV were used for this analysis. In future reports, SV will need to consistently classify roles to ensure better analysis in this area. | No | No | No | No | No | No | No
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled