## PAP Template
Sustainability Victoria
SV Procurement Activity Plan 2021-22
No. | Procurement name | Category | Project | Estimated invitation to supply release date | Market approach (ITS/RFQ/RFT/EOI/ SPC, open/selective) | International Agreement Covered procurement? Yes/No | Comments | Point of contact | Group
1 | RV - Supporting Victorian Councils Evaluation -Materials mapping | Research & evaluation | RV - Supporting Victorian Councils | 2021/22 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
2 | Recycling Victoria Infrastructure Plan building on IV analysis and integrating with SV data system | Consultancy (analysis & advice) | Recycling Victoria Infrastructure | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
3 | Recycling Victoria Infrastructure Plan Cost Benefit analysis of options for key materials | Consultancy (analysis & advice) | RV - Infrastructure Planning | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
4 | Recycling Victoria Infrastructure Plan Editing services | Professional Services | Recycling Victoria Infrastructure | TBC | RFQ | No | Delayed - legislation delayed - updated dates tbc | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
5 | RV - Hazardous Waste Management Plan Hazardous waste management options and research | Research & evaluation | RV - Hazardous Waste Planning | 2021/22 | RFQ | No | This will be 2-3 RFQ's | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
6 | Infrastructure and services options analysis, pilot site assessments and OSP development | Professional Services | Asbestos Disposal Management Plant | 2021-12-01 | RFQ | No | This RFQ involves a PART A and PART B. Lead contractor has option to sub-contract for PART B | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
7 | Communications support with designing and editing communications material | Marketing & Engagement | Asbestos Disposal Management Plant | 2021-07-01 | RFQ | No | This RFQ may be broken into multiple components pending skill set requirement | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
8 | Auditor to develop auditing protocols and conduct audits for asbestos transfer sites | Professional Services | Asbestos Disposal Management Plant | 2021-07-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
9 | Training provider to develop and delivery training modules. | Professional Services | Asbestos Disposal Management Plant | 2021-10-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
10 | Infrastructure expert to conduct site assessments for full network roll out | Professional Services | Asbestos Disposal Management Plant | 2021-10-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Regions & Partnerships
11 | RV – Detox your Home Program | Professional Services | Household Collection Program | 2022-05-01 | Tender | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
12 | RV – Detox your Home Program | Professional Services | Household Collection Program | 2022-05-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
13 | RV – Detox your Home Program | Professional Services | Household Collection Program | 2022-10-01 | RFQ | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
14 | RV - Waste Data New Data System Stage 2 | IT, web and data management | Recycling Industry Support | 2022-06-01 | eServices | No |  | Requestprocurement@sustainability.vic.gov.au | Strategic Foresight & Research
15 | Recycling Victoria Phase 1 creative | Marketing & Engagement | Campaigns | 2021-07-01 | Marketing Services | no |  | Requestprocurement@sustainability.vic.gov.au | Community Action
16 | Recycling Victoria Phase 1 images (part 2) | Marketing & Engagement | Campaigns | 2021-08-01 | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
17 | Recycling Victoria CALD | Marketing & Engagement | Campaigns | 2021-10-01 | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
18 | Recycling Victoria CALD | Marketing & Engagement | Campaigns | 2022-02-01 | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
19 | Recycling Victoria PR | Marketing & Engagement | Campaigns | TBC | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action
20 | Recycling Victoria Phase 2 Creative | Marketing & Engagement | Campaigns | TBC | Marketing Services | No |  | Requestprocurement@sustainability.vic.gov.au | Community Action